## Gantt Chart
PROJECT: Predictive Modelling for Dementia Diagnosis: An Integrative Approach Using Machine Learning and Multi-Dataset Analysis
Chinonso Uche |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
25830651
Project start date: | 2024-06-03 |  |  |  |  | June | [27 empty] | July
Scrolling increment: | 1 | time axis 2024-06-04 to 2024-07-29
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-06-04 to 2024-07-29
Topic Selection
Research Idea and Topic Selection | High Risk | Chinonso Uche | 100% | 2024-06-03 | 14
Literature Review
Collection of Papers on related topic for analysis and review | Goal | Chinonso Uche | 100% | 2024-06-03 | 3 | 2024-06-04: 2; 2024-06-05: 2
Research and analyse existing studies on project topic | Goal | Chinonso Uche | 100% | 2024-06-06 | 7 | 2024-06-06: 2; 2024-06-07: 2; 2024-06-08: 2; 2024-06-09: 2; 2024-06-10: 2; 2024-06-11: 2; 2024-06-12: 2
Data Collection and Preprocessing
Request access and collect datasets from Kaggle and OASIS | On Track | Chinonso Uche | 100% | 2024-06-12 | 7
Preprocess dataset | High Risk | Chinonso Uche | 100% | 2024-06-17 | 21
Interim Report Submission
Review the Interim Report and Submit | Med Risk | Chinonso Uche | 100% | 2024-07-05 | 1
Model Development and Training
Develop and train machine learning models for dementia prediction | Med Risk | Chinonso Uche | 100% | 2024-07-08 | 42
Model Evaluation and Testing
Evaluate and test the performance of the developed models | Low Risk | Chinonso Uche | 100% | 2024-08-19 | 7
Project Report and Documentation
Document project progress, results, and conclusions | High Risk | Chinonso Uche | 100% | 2024-08-26 | 30
Project Submission
Review and Submit Project with Artifact | High Risk | Chinonso Uche | 100% | 2024-09-25 | 3